# Craveva ERP — Production Module: Timeline Summary (for PM)

Context: Laravel/PHP multi-tenant ERP; multi-warehouse already available.

Reference: BIOMIXING_PRODUCTION_DEVELOPMENT_PLAN.md (full Vietnamese report).

Assumptions: 1–2 backend developers (FT) + ~0.5 QA + PM; Hub go-live after UAT on staging; no parallel major projects.

# Table 1 — Go-live scenarios & calendar (wall-clock to Hub)

| Scenario | Scope (Hub go-live) | Dev + integration (est.) | UAT / fix / deploy (buffer) | Total to go-live |
| --- | --- | --- | --- | --- |
| MVP Production | Phases 0 + 1: BOM, batch MVP, production order/batch, RM/FG stock movements by batch (CCP gates not fully enforced) | ~8–12 weeks | +2–3 weeks | ~10–15 weeks (~2.5–4 months) |
| HACCP-ready (Biomixing pilot) | Phases 0 + 1 + 2: add CCP checkpoints, receiving QC, rework, delivery quality lock | ~14–22 weeks | +3–4 weeks | ~17–26 weeks (~4–6.5 months) |
| Full roadmap (§4) | Phases 3–4 on top (sampling/COA, auto project, optional AI API, PRP, audit export, etc.) | +7–13 weeks after Phase 2 | +2–4 weeks | ~6–9 months from kickoff (advanced feature set) |

Suggested Hub milestones

Go-live 1: After MVP — internal / single-site pilot, real batch data.

Go-live 2: After Phase 2 — official production module for HACCP-style gate + inbound QC.

Go-live 3 (optional): Phases 3–4 — AI integration, mandatory COA path, PRP logs, audit exports.

Scope note for PM: If Phase 3 excludes AI/agent API (ERP-only: sampling, COA, auto project, etc.), calendar can be ~4–7 weeks shorter than a Phase 3 scope that includes full AI integration.

# Table 2 — Phase duration (calendar weeks)

| Phase | Content (summary) | Duration (est.) |
| --- | --- | --- |
| 0 | Domain terms, pilot flow, ERD Production ↔ Warehouse ↔ Order | 1–2 weeks |
| 1 | Recipe/BOM, batch traceability MVP, production order/batch, warehouse integration | 6–10 weeks |
| 2 | CCP checkpoints, receiving QC, rework, quality lock on delivery | 5–8 weeks |
| 3 | Sampling + COA, auto project, AI API (optional), storage/location fields | 4–7 weeks |
| 4 | PRP logs, audit export, email approval, etc. | 3–6 weeks |

Multi-warehouse already in place: saves roughly 1–2 weeks vs. greenfield warehouse integration; Phases 1–2 remain heavy (new BOM, production batch, CCP logic).

Main schedule risks: scope changes to BOM/CCP; messy product master data; missing shop-floor specs; Hub tenant data migration for legacy lots.

End of PM summary. Align with BIOMIXING_PRODUCTION_DEVELOPMENT_PLAN.md for architecture and gap details.